Qayyem — Weekly Update, Academic Week 7

Week: 11–15 October 2026

Prepared by: Saif Amro Ibrahim (Team Leader)

Submitted to: Project Supervisor, via Blackboard

# Focus this week

Mobilise for the implementation phase: stand up the GitHub repository the supervisor asked for, fix roles, turn the remaining backlog into assigned issues, and start the two items that sit on the critical path — backend security close-out and hand-marking the evaluation set.

The team confirmed its sequencing: finish and harden the backend first, keeping the current interface as a preliminary shape, then rebuild the frontend properly and give it a proper visual design. The plan is phased accordingly — backend W7–W8, frontend W9–W11, report and defense W12–W14, with a hard backend freeze at the end of Week 8 (IMPLEMENTATION_PLAN.md §3.1).

Submission and defense: Tuesday 1 December 2026 — eight working weeks from now.

# Completed this week

| Member | WP | What was delivered | Evidence (PR / issue / commit) |
| --- | --- | --- | --- |
| Saif | WP0 |  |  |
| Houmood | WP1 |  |  |
| Meshari | WP2 |  |  |
| Salman | WP3 |  |  |
| Mohammed | WP4 |  |  |
| Sultan | WP5 |  |  |

# Planned for next week (Academic Week 8, 18–22 Oct)

| Member | WP | Task | Target |
| --- | --- | --- | --- |
| Saif | WP0 | Issue triage; review queue under 24h; run the backend freeze review on Thursday | Freeze signed off or remainder moved to Future Work |
| Houmood | WP1 | Complete the second marking pass; write evaluation/evaluate.py; report inter-marker agreement | Gold-standard set committed (M2) |
| Meshari | WP2 | Retention-purge audit, error-handling pass, ER diagram, PDPL mapping | WP2 complete at the freeze |
| Salman | WP3 | Finish mockups for all screens; run the mockup usability test; agree the build plan | Findings written up before the rebuild starts |
| Mohammed | WP4 | Edge-case and negative suite; finish the test plan | Committed in DOCUMENTS/ |
| Sultan | WP5 | Chapter 1 complete; Chapter 2 drafting; 6+ sources logged | Ch.1 done |

# Blockers and risks

| Issue | Impact | Owner | Action |
| --- | --- | --- | --- |

# Milestone status

- Next gate: M2 — backend freeze, Thursday 22 October. Days remaining: 12.

- Gate after that: M3 — first accuracy numbers and the new UI shell, 29 October.

- Highest risk this week: the 100-answer marking pass (two markers) and WP2 landing inside two weeks. Both are tracked daily, not weekly.

# Metrics

- Tests passing: 137 / 137 (baseline, verified 10 Oct)

- Open issues: — Closed this week: —

- Commits this week, by member: —

# Questions for the supervisor

- Does the schedule in IMPLEMENTATION_PLAN.md §11 match the official calendar? We have planned to Tuesday 1 December; if the term runs to 8 December we intend to use that week as rehearsal buffer rather than additional scope.

- We plan to keep the current interface as a placeholder until the backend freeze on 22 October, then rebuild the frontend in Weeks 9–11. Is that acceptable for any mid-semester review, given that a demonstration before Week 9 will show the preliminary interface?

- Is a gold-standard set of 100 hand-marked Arabic answers across 3 questions sufficient for the evaluation chapter?

- For the usability test in Week 8, may we approach faculty in the college directly, and is any approval needed before involving them?

- Should the repository be private until submission, or visible to the department throughout?

- §3.2 of the plan records the scope we have trimmed to fit eight weeks. Could you confirm that none of those reductions affects a graded requirement?