## Slide 1
الجامعة السعودية الالكترونية
الجامعة السعودية الالكترونية
28/10/2026
Notes: Progress meeting with Dr. Saeed AlQarni, 28 October 2026.

## Slide 2
College of Computing and Informatics
Information Technology Program
CS489
Senior Project 2 in Computer Science

## Slide 3
Qayyem (قيّم)
Project Supervisor:
Dr. Saeed AlQarni
Saif Amro Ibrahim | S220008133
Houmood Abdulrahman Algoseyer | S230050613
Meshari Abdulrahman Alasmari | S220044964
Salman Ahmed Alharbi | S220042990
Mohammed Jamman Alomari | S220002979
Sultan Bander Altowirgi | S220037005
AI-Powered Arabic Assignment Grading and Feedback System
Notes: Qayyem grades short Arabic answers with a large language model and returns a preliminary score plus formal Arabic feedback for each student.

## Slide 4
Contents
Project Overview
What We Have Built
Results So Far
A Measured Finding: Grading Consistency
Status Against the Plan
Four-Week Plan to the Defense
Risks and Support We Need

## Slide 5
Project Overview

## Slide 6: Project Overview
The problem
Instructors grade short Arabic answers by hand, one at a time.
Feedback reaches students too late to help.
Marking at volume drifts between students.
Our solution
Upload a CSV or Excel file with an ideal answer and rubric.
An LLM gives every student a preliminary score and formal Arabic feedback.
Download the results as an Excel workbook.
Objectives
100 answers graded in under 2 minutes
The same rubric applied to every student
Usable with no technical background
Compliant with the Saudi PDPL
Grades stay preliminary: the instructor reviews them and makes the final decision.
Notes: Scope is short-answer Arabic text. The AI suggests; the instructor decides. The objectives are the ones from Phase 1; the next slides show which are now measured.

## Slide 7
Progress So Far

## Slide 8: What We Have Built: a Working End-to-End System
Sign in
Upload CSV / Excel
AI grading
10 answers per call
Review in Arabic
RTL dashboard
Export to Excel
4 AI providers, one interface
Gemini (default, free tier), OpenAI, Claude and DeepSeek. Switching is a setting, not a code change.
Every AI result is validated
Each returned grade must match a student ID we sent, be in range, and carry feedback.
Privacy by design (PDPL)
Student data is deleted at sign-out or session expiry. API keys are encrypted at rest.
148 automated tests, all passing
They run offline in seconds, so every change is checked before it is merged.
Python 3.12 · Flask 3 · pandas · openpyxl · SQLite · Bootstrap 5 (RTL) · pytest
Notes: Live demo path if asked: sign in, upload sample_responses.csv, watch progress, open results, download Excel. Batching 10 answers per call is what keeps us inside the free tier and fast enough. The validation step guards against the model attributing one student's grade to another.

## Slide 9: Results So Far: Speed Target Met
34 s
to grade 100 answers
target: under 120 s
0
failed grades
out of 360 answers graded
148
automated tests passing
11 new security tests
Chart: Grading time (seconds) by number of answers
| 10 | 50 | 100 | 200
Seconds | 3.5 | 16.9 | 34 | 74.6
Added this week
CSRF protection on every form
Sign-in lockout after 5 failed attempts
Repeatable benchmark script, results saved in the repository
About 0.35 s per answer, growing linearly: about 3 minutes for 500 answers
Notes: Measured 27 Oct 2026 on the real pipeline with Gemini flash-lite (free tier), batch size 10. Three runs at 100 answers gave 37.3, 34.0 and 33.1 seconds. Script: SOURCE/benchmark/benchmark.py; results JSON in SOURCE/benchmark/results.

## Slide 10: A Measured Finding: Grading Consistency
We graded the same answers many times, each copy in a different request, to check that an identical answer always gets an identical score.
Answers per request | Same answer, same score | Largest spread
10 (current) | 2 of 12 | 2 marks / 10
1 | 7 of 8 | 1 mark / 10
Lowering the model temperature from 0.2 to 0 made no difference.
What it means
Batching is what makes grading fast and keeps it inside the free tier.
But neighbouring answers in the same request pull a score by up to 2 marks.
Grading one answer per request is more consistent, but it hit the free-tier rate limit after about 20 calls. The app stopped cleanly and kept the data.
Next: make each score independent of its batch, and verify the change against human marks.
Notes: This is a real limitation we found by measuring, not assuming. It becomes part of the accuracy work in Weeks 11 and 12: compare against two human markers, then fix and re-measure.

## Slide 11
Remaining Work and Plan

## Slide 12: Status Against the Plan
Item | Status | Owner
Working end-to-end system (upload → grade → dashboard → Excel) | Done | Team
Speed target: 100 answers in under 2 minutes (measured 34 s) | Done | Team
Security: CSRF protection and sign-in lockout | Done | Team
GitHub repository (all six members committing) | Partly done | Saif, all
Accuracy vs. human marks (100 answers, 2 markers) | Remaining | Houmood, Salman
Final interface design and rebuild | Remaining | Salman, Meshari
Usability test with 3–5 instructors | Remaining | Salman
Report rewrite (Phase 1 still says GPT-4o only) | Remaining | Sultan, all
User manual (AR/EN) and deployment guide | Remaining | Sultan, Saif
Weeks 7–8 targets (evaluation set, interface mockups) slipped. The plan on the next slide recovers them within four weeks.
Notes: Be direct about the slip: the system and the measurable targets are done; the evidence work (accuracy, usability) and the report are what remain.

## Slide 13: Four-Week Plan to the Defense
Week | Main work | Gate
Week 10 1–5 Nov | Collect and anonymise 100 Arabic answers; two markers start. Interface mockups. Report Ch. 1 and literature sources. | Evaluation set and mockups ready
Week 11 8–12 Nov | Marking done, first accuracy run (AI vs. human). Rebuild main pages. Test plan and failure tests. Ch. 2–3. | First accuracy results
Week 12 15–19 Nov | Consistency fix, Gemini vs. Claude comparison. Usability test with instructors. Deployment guide. Ch. 4–6. | Interface freeze; full draft to supervisor
Week 13 22–26 Nov | Apply supervisor feedback. User manuals, final regression on a clean machine, slides, two rehearsals. | Final report and release
Week 14 29 Nov–1 Dec | Final run-through. | Defense: Tue 1 Dec
Notes: Each item is a GitHub issue with one owner. We send a written update every Thursday before the weekly follow-up. Full draft reaches the supervisor on 19 November.

## Slide 14: Risks and Support We Need
Main risks
Accuracy may be weak against human marks
We report it honestly, with agreement between the two human markers shown first.
Hand-marking 100 answers takes time
Starts in Week 10 with two named markers and a written marking guide.
Uneven contribution (graded individually)
GitHub activity is checked weekly, and tasks are reassigned the same week.
What we need from you
Approval to use Gemini (free tier) as the default model instead of GPT-4o from Phase 1. Other providers remain selectable.
Advice on obtaining real, anonymised student answers for the evaluation set.
Agreement on the weekly follow-up: a written update every Thursday, with links to the work.
Notes: Close by asking for these three decisions; they unblock Week 10.

## Slide 15
Thank You